## Risk Register
RISK REGISTER
Olist Brazilian E-Commerce Dataset ¦ 2016–2018 ¦ BA Portfolio Project
# | Risk Name | Cause / Description | Consequence | Likelihood | Impact | Risk Rating | Mitigation Strategy | Owner | Status
1 | Delivery & Logistics Risk | Carrier inefficiencies and regional infrastructure gaps cause shipment delays and in-transit damage. States AL, MA, PI show significantly worse performance than the national average. | Late or damaged deliveries directly drive 1-star reviews. Data shows an 0.87 correlation between late delivery and 1-star ratings, affecting brand reputation and repeat purchase rate. | Medium | High | High | Introduce regional carrier SLA monitoring. Flag underperforming states (AL, MA, PI) for priority review. Set delivery time accuracy KPIs and escalation triggers at 7% late rate threshold. | Logistics Team | Open
2 | Product Quality Risk | Olist operates as a 3rd-party marketplace — product quality relies entirely on seller standards with no centralised pre-shipment quality check by Olist. | Office Furniture shows a 20.5% 1-star rate even on on-time deliveries, confirming product quality as an independent driver of negative reviews separate from delivery issues. | Medium | High | High | Introduce seller quality scorecards. Flag high-risk categories (e.g. Office Furniture). Require photo verification for listings in categories with >15% 1-star rate. | Seller Relations | Open
3 | Marketplace Supply Risk | Introducing stricter seller quality thresholds or increased compliance requirements may deter smaller or lower-rated sellers from listing on the platform. | Reduction in total product listings, narrowing catalogue breadth and reducing platform competitiveness against larger marketplaces with higher SKU counts. | High | High | Critical | Phase quality controls gradually. Offer seller support programmes before enforcement. Monitor listing volume monthly and set a minimum catalogue size threshold before tightening standards. | Product & Strategy | Open
4 | Change Implementation Risk | Operational changes to delivery routing or carrier contracts may introduce transitional disruptions, causing short-term increases in delays during the switchover period. | Attempted improvements to the logistics system could temporarily worsen the very problem they aim to solve, increasing the 1-star review rate in the short term. | Low | High | Medium | Pilot logistics changes in one low-risk region before national rollout. Define clear rollback criteria. Track review scores weekly during any transition period. | Operations | Open

## Tiers
RISK RATING
Critical | High Likelihood + High Impact — immediate action required
High | Medium Likelihood + High Impact — priority mitigation needed
Medium | Low Likelihood + High Impact — monitor and plan response
Low | Low Likelihood + Low Impact — accept with periodic review